## ME-408
LOT 6459 TONGAAT, SEATIDES,
172-188 GENAZANO ROAD
ALTERATIONS AND ADDITIONS
IMMANUAL CHURCH
DATE: 11 FEBRUARY 2026
PROVISIONAL BILLS OF QUANTITIES
ITEM NO |  |  | QUANTITY | RATE | AMOUNT
BILL NO. 01
PRELIMINARIES
1 | Establishment | Item | 1 | 85000 | 85000
2 | Site Preliminaries and office overheads + QS measure sched of quants | Mnths | 6 | 85000 | 510000
2 | Contract Works Insurances--Existing Building-- Excluded CLIENT TO DO | Item
3 | Public Liability Insurances By Builder | Item | 1 | 3500 | 3500
4 | Site Toilets | Mnths | 6 | 1000 | 6000
| TOTAL PRELIMINARIES AND GENERAL |  |  |  | 604500
BILL NO. 1
ALTERATIONS
Breaking up and removing
1 | Break/demolish existing columns/piers and cart away | No | 4 | 850 | 3400
2 | Break existing surface bed (100mm thick assumed) | m² | 10.65 | 1750 | 18637.5
Demolishing and carting away
3 | Planter wall | m | 7 | 175 | 1225
4 | Demolish existing Staircase | m² | 6 | 450 | 2700
Taking down and removing
5 | Demolish existing walls and cartaway | m² | 21 | 180 | 3780
6 | Remove and reposition existing single timber door | No | 1 | 650 | 650
7 | Existing rwdp catch pit repositioned | No | 1 | 1250 | 1250
Bricking up and making good
8 | Brickup openings | m² | 3 | 950 | 2850
Make good existing walls
9 | Making good existing walls including painting (skim and paint) - downstairs area only | m² | 567 | 150 | 85050
10 | Allowance for making good existing staircase | m² | 9 | 250 | 2250
11 | Allowance for new floor finishes to existing staircase (R 200/m2 PC for tiling) | m² | 15 | 490 | 7350
12 | Provision for repairs to cracks across site | sum | 1 | 15000 | 15000
Expose existing foundations
13 | Existing foundation to be exposed and dimensions measured. including making good once work/measuring is finished | m³ | 2 | 550 | 1100
Drill and dowel new slab to existing
14 | Drill and dowel chemical anchors into existing suspended slab to Engineer's details | m | 19 | 1500 | 28500
| TOTAL ALTERATIONS |  |  |  | 173742.5
BILL NO. 2
EARTHWORKS, ETC.
For preambles see "Model Preambles for Trades 2017"
EXCAVATION
Excavation in earth not exceeding 2m deep
1 | Excavate for ground beams and pads | m³ | 39 | 110 | 4290
2 | Reduce levels under surface beds | m³ | 21 | 100 | 2100
Excavate back from the vertical face of excavations to the extent required for the insertion and removal of formwork and afterwards return, fill in and ram.
3 | Excavate back from the face of ground beam excavations exceeding 500 mm and not exceeding 1,5 m deep and 300 mm between the structure and the sides to be excavated back. | m² | 4 | 110 | 440
Risk of collapse of excavations other than bulk:
4 | Sides of trench and hole excavations not exceeding 1,5m deep | m² | 76 | 10 | 760
CARTING AWAY.
Extra over all excavations for loading, carting and dumping surplus excavated material (no allowance made for increase in bulk):
5 | Off site to a dumping site to be found by the Contractor | m³ | 15 | 150 | 2250
EARTH FILLING, ETC.
Compaction of in situ surfaces:
6 | Rip and recompact ground surface, including scarifying for a depth of 150mm, breaking down oversize material, adding suitable material where necessary and compacting to 90% modified AASHTO density and trim to required levels. | m² | 105 | 50 | 5250
Filling with material from the excavations compacted to a density of at least 95% Mod. AASHTO maximum density:
7 | Backfilling to trenches, holes, etc. | m³ | 23 | 90 | 2070
Filling with approved material G5 quality supplied and carted onto site by Contractor, compacted to a density of at least 98% Mod. AASHTO maximum density:
8 | Under surface beds | m³ | 11 | 850 | 9350
9 | Under ground beams/footings and pads | m³ | 5 | 850 | 4250
KEEPING EXCAVATIONS FREE OF WATER
Keeping excavations free of water
10 | Allow for keeping excavations free of water by hand or machinery. | Item | 1 | 2000 | 2000
TESTS
Prescribed density tests on filling:
11 | Modified AASHTO Density test | Item | 1 | 1000 | 1000
SOIL POISONING
Soil insecticide:
12 | Under floors and foundations etc. including forming and poisoning shallow furrows against foundation walls etc, filling in furrows and ramming | m² | 186 | 17 | 3162
| TOTAL EARTHWORKS |  |  |  | 36922
BILL NO . 3
CONCRETE, FORMWORK AND REINFORCEMENT
For preambles see "Model Preambles for Trades 2017"
UNREINFORCED CONCRETE
15MPa/19mm concrete
1 | Surface blinding | m³ | 2 | 1800 | 3600
REINFORCED CONCRETE CAST AGAINST EXCAVATED SURFACES
25Mpa/19mm concrete
2 | Ground beams | m³ | 9 | 2050 | 18450
3 | Concrete pads | m³ | 2 | 2050 | 4100
REINFORCED CONCRETE
30Mpa/19mm concrete
4 | Surface beds | m³ | 11 | 2200 | 24200
5 | Columns, stiffener piers and infill to brick pier | m³ | 4.6632 | 2200 | 10259.04
6 | Beams | m³ | 7 | 2200 | 15400
7 | Slabs and inverted beams | m³ | 23 | 2200 | 50600
CONCRETE SUNDRIES
Test Cubes
8 | Making and testing set of three 150 x150 x 150mm concrete strength test cubes | No | 12 | 165 | 1980
Finishing top surfaces of concrete smooth with a steel float
9 | to top of slabs | m² | 93 | 20 | 1860
Finishing top surfaces of concrete smooth with a wood float
10 | Surface beds, stair landings and treads etc | m² | 71 | 20 | 1420
ROUGH FORMWORK
Rough formwork to sides
11 | Ground beams | m² | 24 | 250 | 6000
12 | Pads | m² | 4 | 250 | 1000
13 | Formwork to columns and stiffener piers with total height not exceeding 3.5m | m² | 53.94 | 350 | 18879
14 | to edges n.e 300mm high, propped up not exceeding 3.5m | m | 49 | 130 | 6370
Rough formwork to sides and soffits
15 | To isolated beams | m² | 68 | 450 | 30600
Rough formwork to soffits
16 | Slabs not exceeding 250mm thick propped up, exceeding 1.5m not exceeding 3.5m high from bearing level. | m² | 93 | 250 | 23250
MOVEMENT JOINTS ETC
Movement joints with "Jointex" between vertical concrete and Construction Joints
17 | Isolation joint, 10mm jointex sealed with polysulphide sealant to manufacturer's specifiction | m | 41 | 40 | 1640
Saw cut joints
18 | 3 x 60mm Saw cut joints in top of concrete | m | 14 | 30 | 420
REINFORCEMENT (PROVISIONAL)
Mild steel reinforcement to structural concrete work
19 | Bars in various diameters ( assumed various kg/m3 as per Engineer) | t | 7.0028 | 17000 | 119047.6
Fabric reinforcement to surface beds only
20 | Type 254 fabric reinforcement in concrete surface beds, slabs, etc | m² | 71 | 85 | 6035
| TOTAL CONCRETE FORMWORK AND REINFORCEMENT |  |  |  | 345110.64
BILL NO. 4
MASONRY
For preambles see "Model Preambles for Trades 2017"
SUBSTRUCTURE
14 Mpa Clay Maxi bricks
1 | 230mm walls | m² | 22 | 630 | 13860
SUPERSTRUCTURE
7 Mpa Clay Maxi bricks
2 | 115mm walls | m² | 100 | 315 | 31500
3 | 115mm in beam filling | m² | 12 | 315 | 3780
4 | 260mm walls (including areas where existing brickwork is raised) | m² | 437 | 630 | 275310
5 | Feature signage wall (brick pier) | m² | 21.6 | 630 | 13608
6 | Piers, 270 x 230mm wide, in common brickwork (above concrete rafter beam) | No | 12 | 375 | 4500
Brickwork reinforcement
7 | 75mm Wide reinforcement built in horizontally | m | 336 | 4 | 1344
8 | 150mm Wide reinforcement built in horizontally | m | 1375.8 | 6 | 8254.8
Prestressed fabricated lintels
9 | 110 x 70mm Lintels in lengths not exceeding 3m | m | 164 | 75 | 12300
Brickwork sundries
10 | Brixeal bituminous compound emulsion paint to walls | m² | 458.6 | 35 | 16051
| TOTAL MASONRY |  |  |  | 380507.8
BILL NO. 5
WATERPROOFING
For preambles see "Model Preambles for Trades 2017"
DAMP PROOFING OF WALLS AND FLOORS
Gundle® API Brikgrip® DPC 250um' damp proof course (SANS 952-12011):
1 | On walls, stepped up in cavities, under cills, etc. | m² | 38 | 120 | 4560
'Gundle® API A.T USB Green' 375um membrane to SANS 952-1:2011 laid with minimum 150mm overlaps and sealed with 'Gunplas®' pressure sensitive tape:
2 | Under surface bed | m² | 71 | 40 | 2840
| TOTAL WATERPROOFING |  |  |  | 7400
BILL NO. 6
CARPENTRY AND JOINERY
For preambles see "Model Preambles for Trades 2017"
TIMBER DOORS ETC.
Internal doors to Architect's specification
1 | D04- Internal door - Flush Panel semi solid internal door and installation complete | No | 1 | 1180 | 1180
2 | D06-Internal door - Flush Panel semi solid internal door and installation completeupply (based on the PC rate) and installation complete | No | 1 | 1180 | 1180
3 | D07- Internal door - Flush Panel semi solid internal door and installation complete | No | 1 | 1180 | 1180
4 | D08- Internal door - Flush Panel semi solid internal door and installation complete | No | 1 | 1180 | 1180
5 | D09-Internal door - Flush Panel semi solid internal door and installation complete | No | 1 | 1180 | 1180
6 | D10- Internal door - Flush Panel semi solid internal door and installation complete | No | 1 | 1180 | 1180
External doors to Architect's specification
7 | D12- Solid external door and installation complete | No | 1 | 4000 | 4000
Frames
8 | Internal single door frame installed complete including priming of back of frames | No | 6 | 1414.3 | 8485.8
9 | External single door frame installed complete including priming of back of frames | No | 1 | 2200 | 2200
Skirtings
10 | Allowance for Skirtings (PC rate R 45/m ex vat). Supply and install complete | m | 220 | 80 | 17600
| TOTAL CARPENTRY AND JOINERY |  |  |  | 39365.8
BILL NO. 7
CEILINGS AND PARTITIONS
For preambles see "Model Preambles for Trades 2017"
SUSPENDED CEILINGS
9.5mm gypsum plasterboard ceiling inclusive of all substructure as required, fixed to underside of SA pine roof trusses to specialist details
1 | Internal ceilings | m² | 143 | 305 | 43615
2 | Extra over ceiling for 1000 x 1000mm trap door | No | 2 | 1550 | 3100
RAKED CEILINGS
9.5mm gypsum plasterboard ceiling inclusive of all substructure as required, fixed to underside of SA pine roof trusses to specialist details
3 | Internal ceilings | m² | 222.2 | 350 | 77770
EAVES CEILINGS
Nutec ceilings to eaves
4 | To eaves | m² | 44.1 | 380 | 16758
CORNICES ETC
Shadowline cornices to Interior designers specification
5 | 20mm Shadowline cornice | m | 242 | 95 | 22990
6 | Wall angle to external eaves installation | m | 72 | 55 | 3960
Insulation to ceilings
7 | Insulation to Architect specification | m² | 383.46 | 105 | 40263.3
PARTITIONS ETC
DRYWALL PARTITIONS
Partitions consisting of 51mm studs with 12,5mm thick Gypsum plasterboard on both sides (fully skimmed with suitable product as required by the Architect), with vertical supports at minimum 600mm centres (or as per manufacturers recommendation) including 50mm mineral wool insulation for acoustic enhancement. The Contractor shall include all abutments, accessories and any other configurations as required on site in the rate below
8 | Partitions 3000mm high with bottom and top tracks plugged | m | 4 | 1741.65 | 6966.6
| TOTALCEILINGS AND PARTITIONS |  |  |  | 215422.9
BILL NO 8
FLOOR COVERINGS
Berber point 650 - 50cmx50cm Carpet tiles
1 | To internal floors | m² | 261 | 375.4789 | 98000
| TOTAL FLOOR COVERINGS |  |  |  | 98000
BILL NO. 9
PLASTERING
For preambles see "Model Preambles for Trades 2017"
SUPPLEMENTARY PREAMBLES
INTERNAL PLASTER
Cement plaster on brickwork
1 | On walls | m² | 651.7 | 100 | 65170
2 | Narrow widths | m² | 65.17 | 150 | 9775.5
EXTERNAL PLASTER
Cement plaster on brickwork
3 | On walls | m² | 441.7 | 100 | 44170
4 | To existing facebrick walls | m² | 309 | 100 | 30900
5 | Narrow widths | m² | 44.17 | 150 | 6625.5
Extra over for Feature plaster finish
6 | Feature plaster | m² | 7 | 250 | 1750
CONCRETE SURFACES
Cement plaster on concrete surfaces
7 | Beams | m² | 68 | 150 | 10200
8 | Columns and stiffeners | m² | 49 | 150 | 7350
9 | Soffits of slabs | m² | 93 | 100 | 9300
SCREEDS
Screeds on concrete
10 | 40mm Thick on floors | m² | 441 | 130 | 57330
11 | Decorated/Self levelling screed | m² | 87 | 580 | 50460
| TOTAL PLASTERING |  |  |  | 293031
TILING
BILL NO. 10
For preambles see "Model Preambles for Trades 2017"
FLOOR TILING
PC Allowance for Tile @ R250/m2 and allow to take delivery thereof, storage, profit and mark-up and fixing with adhesive to screed (screed elsewhere) and flush pointed with tinted (waterproof) grout
1 | To internal floors | m² | 73 | 560 | 40880
| TOTAL TILING |  |  |  | 40880
BILL NO. 11
PLUMBING AND DRAINAGE
For preambles see "Model Preambles for Trades 2017"
Note: The Contractor shall price all first and second fix plumbing items with all necessary pipework considered in terms of reticulation between points internally, as well as the pipework required from the external perimeter of the house. All external plumbing priced separately and is elsewhere.
FIRST AND SECOND FIX PLUMBING INSTALLATION OF SANITARY FITTINGS INCLUDING RETICULATION AND WASTE PIPEWORK FOR ALL WORK REQUIRED UP TO EXTERNAL ENVELOPE
Wash Hand Basins (WHB)
1 | First and Second fix plumbing including all necessary pipework, hot and cold water supplies complete (Sanitary Fitting elsewhere) | No | 1 | 4150 | 4150
Toilets (WC)
2 | First and Second fix plumbing including all necessary pipework, hot and cold water supplies complete (Sanitary Fitting elsewhere) | No | 1 | 4350 | 4350
Sink
3 | First and Second fix plumbing including all necessary pipework, hot and cold water supplies complete (Sanitary Fitting elsewhere) | No | 1 | 4150 | 4150
Prep bowl
4 | First and Second fix plumbing including all necessary pipework, hot and cold water supplies complete (Sanitary Fitting elsewhere) | No | 1 | 4150 | 4150
Geysers
4 | First and Second fix plumbing including all necessary pipework, hot and cold water supplies complete (Sanitary Fitting elsewhere) | No | 1 | 4150 | 4150
5 | General plumbing allowance including connection to existing system | Item | 1 | 30500 | 30500
| TOTALPLUMBING AND DRAINAGE |  |  |  | 51450
BILL NO. 12
PAINTWORK
For preambles see "Model Preambles for Trades 2017"
FLOATED PLASTER SURFACES
Primed and painted with two coats Plascon Wall and All to be applied in strict accordance with manufacturers specifications, colour to be confirmed by Architect
1 | Internal walls | m² | 651.7 | 80 | 52136
2 | Narrow widths | m² | 65.17 | 150 | 9775.5
FLOATED PLASTERED CONCRETE SURFACES
Primed and painted with two coats Plascon Wall and All to be applied in strict accordance with manufacturers specifications, colour to be confirmed by Architect
3 | Beams | m² | 68 | 80 | 5440
4 | Columns | m² | 46 | 80 | 3680
5 | Soffits | m² | 93 | 80 | 7440
Primed and painted with two coats Plascon Wall and All to be applied in strict accordance with manufacturers specifications, colour to be confirmed by Architect
5 | External walls | m² | 757.7 | 80 | 60616
6 | Narrow widths | m² | 44.17 | 80 | 3533.6
WOOD SURFACES
One coat oil wood primer, one coat universal undercoat and two coats super universal enamel paint on
7 | Doors | m² | 34 | 120 | 4080
8 | Door frames, etc | m² | 4 | 100 | 400
9 | Timber skirting | m | 220 | 25 | 5500
ON PLASTER BOARD
Primer, undercoat and two top coats Plascon Wall and All as per manufacturers specifications
10 | On ceilings and cornices externally | m² | 365.2 | 80 | 29216
11 | To Nutec ceilings externally | m² | 44.1 | 120 | 5292
12 | Partitions | m² | 4 | 80 | 320
| TOTAL PAINTWORK |  |  |  | 187429.1
BILL NO. 13
SUBCONTRACT PACKAGES
ELECTRICAL INSTALLATION, LIGHT FITTINGS, PLUGS AND SWITCHES
1a | Electrical installation | Item | 1 | 287405 | 287405
1b | Three phase Upgrade - Optional | Item | 1 | 46400 | 46400
TIMBER STAIRCASE AND TIMBER DECK
2 | Timber staircase and Timber deck construction | Item | 1 | 103655 | 103655
ALUMINIUM WINDOWS AND DOORS/LOUVRES
3 | Aluminium windows and doors | Item | 1 | 302123.93 | 302123.93
ROOF SUPPLY AND INSTALLATION
4 | Roof Supply and Installation | Item | 1 | 477690.6 | 477690.6
METAL PALISADE/GATE
5 | GMS screen and gate | Item | 1 | 38510.6 | 38510.6
BALUSTRADES
6 | Balustrades | Item | 1 | 17556.93 | 17556.93 | 1950.77
RAINWATER GOODS
7 | Rainwater goods | Item | 1 | 29700 | 29700
TIMBER SCREEN
8 | Timber screen | Item | 1 | 49140 | 49140
| TOTAL SUBCONTRACT PACKAGES |  |  |  | 1352182.06
BILL NO. 14
PROVISIONAL SUMS
IRONMONGERY
1 | Provisional allowance for Ironmongery of R 15,000 ex vat | Item | 1 | 15000 | 15000
LANDSCAPING
2 | Provisional Allowance for Landscaping of R 25,000 ex Vat | Item | 1 | 25000 | 25000
SANWARE/BRASSWARE/GEYSERS/GAS GEYSER ETC.
3 | Provisional allowance for sanware/brass ware/geysers of R 30,000 ex Vat | Item | 1 | 30000 | 30000
MIRRORS AND BATHROOM ACCESSORIES
4 | Provisional allowance for Mirros and bathroom accessories of R 5,000 ex vat | Item | 1 | 5000 | 5000
SIGNAGE
5 | Provisional allowance for Signage of R 10,000 ex vat | Item | 1 | 10000 | 10000
SEWER
6 | Provisional allowance for Sewer of R 15 000 ex vat | Item | 1 | 15000 | 15000
FEATURE WALL SIGNAGE
7 | Provisional allowance for Timber screen (referenced as repurpose existing on drawing) of R 5 000 ex vat | Item | 1 | 5000 | 5000
STAGE
8 | Provisional allowance for Stage of R 40 000 ex vat | Item | 1 | 40000 | 40000
JOINERY FOR SOUND AND MEDIA
9 | Provisional allowance for Joinery for sound and media of R 35 000 ex vat | Item | 1 | 30000 | 30000
| TOTAL PROVISIONAL SUMS |  |  |  | 175000
1 | ALTERATIONS |  |  |  | 173742.5
2 | EARTHWORKS |  |  |  | 36922
3 | CONCRETE FORMWORK AND REINFORCEMENT |  |  |  | 345110.64
4 | MASONRY |  |  |  | 380507.8
5 | WATERPROOF |  |  |  | 7400
6 | CARPENTRY AND JOINERY |  |  |  | 39365.8
7 | CEILINGS |  |  |  | 215422.9
8 | FLOOR COVERINGS |  |  |  | 98000
9 | PLASTERERING |  |  |  | 293031
10 | TILING |  |  |  | 40880
11 | PLUMBING |  |  |  | 51450
12 | PAINTWORK |  |  |  | 187429.1
13 | SUBCONTRACT PACKAGES |  |  |  | 1352182.06
14 | PROVISIONAL SUMS |  |  |  | 175000
| TOTAL BUILDERS WORK |  |  |  | 3396443.8
BILL NO. 1
WALKWAYS
For preambles see "Model Preambles for Trades 2017"
WALKWAY PAVING
Site Clearance
1 | Clear and grub within road reserve | m² | 12 | 15 | 180
Excavations
2 | Excavate to reduce levels for layer works installation (elsewhere) | m³ | 4 | 100 | 400
Compaction
3 | Rip and re-compact excavated surface to Minimum 93% of Mod. AASHTO density | m² | 12 | 40 | 480
Filling with approved material G5 quality supplied and carted onto site by Contractor, compacted to a density of at least 100% Mod. AASHTO maximum density:
4 | to walkway areas | m³ | 2 | 750 | 1500
Bedding to Engineer's details
6 | 20mm sand | m³ | 1 | 700 | 700
Concrete pavers
7 | laid to architects detail on river sand (elsewhere) - R 300/m2 ex vat PC | m² | 12 | 530 | 6360
| TOTAL WALKWAYS |  |  |  | 9620
BILL NO. 2
STORMWATER
For preambles see "Model Preambles for Trades 2008"
Earthworks
1 | Excavate for pipe trenches not exceeding 2m deep | m³ | 27.746 | 100 | 2774.6
2 | Backfilling to pipe trenches | m³ | 12.4127 | 110 | 1365.4
3 | Selected granular filling in bedding under and filling around pipes | m³ | 6.5714 | 100 | 657.14
UPVC storm water pipes
4 | 110mm UPVC pipes | m | 46 | 192.62 | 8860.52
Extra over 110mm pipes for:
5 | Bends | No | 3 | 139.08 | 417.24
6 | Junctions | No | 1 | 188.54 | 188.54
Channels
7 | Concrete stormwater channel | m | 17 | 750 | 12750
SUNDRIES
Connections
8 | Connect to existing services | Item | 1 | 2500 | 2500
Testing
9 | Testing of the whole system | Item | 1 | 3500 | 3500
| TOTAL STORMWATER |  |  |  | 33013.44
1 | DRIVEWAYS AND WALKWAYS |  |  |  | 9620
2 | STORMWATER |  |  |  | 33013.44
| TOTAL EXTERNALWORKS |  |  |  | 42633.44
1 | PRELIMINARIES AND GENERAL |  |  |  | 604500
2 | BUILDING |  |  |  | 3396443.8
3 | EXTERNAL WORKS |  |  |  | 42633.44
| TOTAL EX VAT |  |  |  | 4043577.24
| Markup @ 7,5% |  |  |  | 303268.293
| TOTAL INCLUDING MARKUP |  |  |  | 4346845.533
| VAT @ 15% |  |  |  | 652026.8299
| TOTAL INCLUDING VAT |  |  |  | 4998872.3629